## Master Review Tracker
S.No | Report Name | Review Comment / Issue Raised | Developer Name(Fixed By) | Resolution Status | Technical Resolution / Coding Explanation | SQL / BIRT File Name(s)
1 | AFOP | Report is blank; expecting data.
2 | CA Income | Report is blank; expecting data. | Siva | Fixed | Verified in both Local and Production environments. Report is no longer blank. Expected records are populated successfully.
3 | TP - DR | Missing data. Expected more breaks. | Siva | Fixed | Issue resolved. TP-DR report now returns the expected breaks. Validation completed and confirmation already shared through a separate email.
4 | TP - Settlement | Missing data. Expected more breaks. | Siva | Fixed | Issue resolved. TP-Settlement report now returns the expected break records. Validation completed and confirmation already shared through a separate email.
5 | MFS | Missing data. Summary page not matching break page. | Siva | Fixed | Converted the original MS Access/MS SQL logic into BIRT SQL without changing the business logic. Summary and detail tabs populate correctly as per the source Access DB.
6 | CA Mandatory | Missing data. Expected more breaks. | Siva | Fixed | CA Mandatory report is returning data correctly and working as expected.
7 | Weekly MF Escalation Report (Non Hedge) | Summary buckets incorrect; hedge items included. | Siva | Fixed | Root cause identified. Original Access DB logic did not exclude Hedge items for the Non-Hedge report. Dataset logic was modified to exclude Hedge records. Now only Non-Hedge records are displayed.
8 | Weekly MF Escalation Report (Hedge) | Summary buckets incorrect; summary/detail mismatch. | Siva | Verified | Revalidated against the original Access DB/MS SQL query. The implemented SQL matches the source logic. No coding discrepancy found during verification.
9 | Management Reporting | Need explanation of 60+ sheets criteria. | Siva | Fixed | Issue resolved. Management Reporting criteria verified and working as expected. Latest report files have been prepared and moved to the deployment folder for SmartStream deployment.
10 | SEB Researching Account Discrepancy | Report blank; need criteria / breaks exist in TLM. | Siva | Fixed
11 | SEB MF Fractional Breaks | Currency blank/mismatch between report and TLM counts. | Siva | Fixed | Dataset logic corrected. Currency values are now populated correctly and report count matches expected output.
12 | SEB MF Fractional Breaks | 1344 fractionals; report blank currency 1329 vs TLM 127 blank. Investigate count mismatch. | Siva | Fixed | Currency blank issue resolved by correcting dataset logic. Report is now working as expected.
13 | TP Reports | TP-D&R: TLM=21 vs Report=4. TP-Settlement: TLM=855 vs Report=847. | Siva | Verified | TP reports validated and confirmed working as expected. No further code changes required.
14 | Zero_Pos | Quarterly Breaks showing as blank | Siva | Fixed | Now Quarterly Breaks tab also working.
15 | Master Break Reporting | Discovery Age/System Entry Date; duplicates; FS exception; Vestima; child break sign. | Lokesh
16 | AFP Accounts Weekly Progress | Report blank; expecting results. | Lokesh
17 | AFP Capital | Showing resolved breaks only; should show unresolved. | Lokesh
18 | AFP Chile | Showing resolved breaks only; should show unresolved. | Lokesh
19 | AFP Cuprum | Showing resolved breaks only; should show unresolved. | Lokesh
20 | AFP Modelo | Showing resolved breaks only; should show unresolved. | Lokesh
21 | AFP Planvital | Showing resolved breaks only; should show unresolved. | Lokesh
22 | AFP Provida | Showing resolved breaks only; should show unresolved. | Lokesh
23 | AFP Uno | Showing resolved breaks only; should show unresolved. | Lokesh

## Status Legend
Resolution Status | Instructions
Fixed | Fill Technical Resolution, SQL/BIRT files modified, and remarks for each issue.
Pending
Need Clarification
Not Applicable